## Slide 1
Operations Request Tracker and Reporting
Personal portfolio simulation | Synthetic data | 7 October 2026
01
Teams receiving requests through different channels need one reliable view of owners, target dates and next actions.
The reporting question
Which items need manager attention now, and which records need correction before we trust the report?
Scope: 36 fabricated requests received 1 September to 6 October 2026.
Notes: This is a personal portfolio simulation. The requests and roles are fictional; no real team supplied data or approved the suggested process.

## Slide 2
Main findings
Personal portfolio simulation | Synthetic data | 7 October 2026
02
36
total requests
22
open
9
overdue
6
blocked
Status breakdown: 7 New 9 In Progress 6 Blocked 14 Completed
Blocked and overdue groups can overlap. Completed items are excluded from the open count.
Notes: All figures are from the synthetic Requests records and the workbook Summary at 7 October 2026. Open is any status other than Completed. Overdue is open with target before the as-of date.

## Slide 3
Important issues and risks
Personal portfolio simulation | Synthetic data | 7 October 2026
03
2 requests have no owner
DS-021 and DS-032 need an assignment before follow-up is accountable.
2 records need data correction
DS-033 lacks a closed date. DS-034 has an impossible target date and is counted overdue pending correction.
6 open requests have High priority. Targets are planning assumptions, not official service standards.
Notes: The two inconsistent records were deliberately included to test quality checks. Do not silently change source information in real use. The counts describe synthetic requests, not measured operational performance.

## Slide 4
Options for manager review
Personal portfolio simulation | Synthetic data | 7 October 2026
04
Option 1 Informal follow-up
Low coordination effort; exceptions may remain unclear.
Option 2 Weekly owner-led exception review
Review overdue and blocked items, assign missing owners and repair flagged fields.
Option 3 Automate reminders now
Could standardize prompts, but status and target rules have not been confirmed.
Recommendation: trial option 2 for four weeks before considering automation.
Notes: The proposed 20-minute weekly review and four-week trial are effort assumptions, not observed costs or benefits. The recommendation follows from 9 overdue, 6 blocked, 2 missing-owner and 2 inconsistent records.

## Slide 5
Next actions and decision
Personal portfolio simulation | Synthetic data | 7 October 2026
05
1 Assign owners to DS-021 and DS-032.
2 Review overdue and blocked items with their fictional role owners.
3 Verify DS-033 and DS-034 before correcting the tracker.
Decision required
Approve or decline a four-week weekly review and agree how target changes and unresolved blockers will be recorded.
Notes: A manager in this fictional exercise would name a coordinator and approve the review. No actual manager or stakeholder has been asked, and no decision has been made.